## Timesheet
Summer 2016 Timesheet
Student Name: Xiangyu Li | [12 empty] | Project: Objective C Team
Work Week | Team Meeting | Write/Update Project Plan | Track and Report Project/Team Status | Communication (email, chat, phone, etc.) | Understand and Document Requirements | Research | Documentation (Specify Document in Comments) | Study Source Code | Architecture or Design (New or Existing Code) | Implementation (Code) | Implement Unit Tests | Review Code (After changes) | Write Test Plan | Write Test Cases and Document Test Results | Run Test Cases | Other (Clarify in Comments) | Comments | Week Summary
5/26/16 - 6/1/16 | 2 |  |  | 3 | 8 |  |  | 5 | [7 empty] | 2 | Team meeting with teammates and know each other. Communication with instructor and teammates. Read the manual and relative documents. Read source code. Compiled the UCC in Linux, Windows and Mac OSX | This week I installed and compiled the UCC on several Oss. After that I tested
6/2/16 - 6/8/16 | 3 | 1 |  | 3 | 7 |  |  | 6 | [8 empty] | This week, I attend the team meeting for 3 hours discussing about the project. I with my teammates wrote and initialized the project plan for 1 hour and the weekly team document at the same time. I have contacted with teammates and instructor by Piazza/Emails/Wechat for 3 hours. Read "UCC Software Design" twice for 2 hours. Read "RequirementTutorial" for 2 hours. Read "Presentations" "SVNrules" "GradeBreakDown" "Project Folder Structure" "DefectLog" "TestCaseTemplate" for 3 hours. Read 2010-3-fall "counting_standard-ObjectiveC" and "ObjectiveC Code Count",and compare the difference between them for 4 hours Read 2010-3-fall "Project Plan" and "Test Plan" for 2 hours | Have meeting with my teammates and have a overview about what to do and how to do the project.
6/9/16 - 6/15/16 | 8 | 1 |  | 1 | 5 |  |  | 9 | [8 empty] | This week, we had 2 4-hour meetings and in the first one we set up the environment of code to program in the future. In the second 4-hour meeting, we discussed and fixed most of compile errors when take 2011 code to 2014 version. 1 hour for update the team plan. 1 hour for communication online. 5 hours for re-read the documents in 2011 and 2014 to know what have been down in 2011 and what should we do for 2014. 9 hours for read code and take clear about the code in an overview. | There are 41 .h files and 42 .cpp files in 2014 version. I fixed bug with teammates when add 2011 code to 2014(there is still a linking error because the change of common function in 2014). I made the trello for ObjectiveC team to track bugs, to-dos, doing
6/16/16 - 6/22/16 | 8 | 1 |  | 2 |  |  |  | 4 |  | 2 |  | 1 | 2 |  |  |  | This week, we had 2 4-hour meetings and in the first one we fixed the linking error. In the second one, we made a test plan and updated our team plan for 1 more hour. 2 hours for communicating with teammates. 4 hours for study source code. 2 hours for changing code and check with code before for 1hour. 2 hours for helping teammates to write test plan. | This week we fixed the linking error and figured out where were changed in 2011 to 2014. Add code for 2011 Objc files and made a test plan for it.
6/23/16 - 6/29/16 | 12 | 1 | [11 empty] | 4 | 4 |  | This week we meet 3 times and run test cases in 2011 compatible to 2014. Also we fix the extension problems when extensions sharing with other languages. | We find some difference in 2011 and 2014 baselines and also we need to discuss different approaches of dealing with extensions
6/30/16 - 7/6/16 | 8 | 1 | [10 empty] | 3 | 4 | 4 |  | This week, we had 2 4-hour meetings and in the first one we fixed the extension approach as instructor said. In the second one, we finished the regression test and the new features test . 3 hours for helping teammates to write test plan. 4 hours for helping teammates to write test case. 4 hours for writing test case documents. | We have finished the code and test for being compatible to 2014.
7/7/16 - 7/13/16 | 8 | 1 | [5 empty] | 6 |  |  |  | 3 |  |  |  | 2 | This week, we had 2 4-hour meetings. In the first one, we make the objective c counter compilable in 2015 baseline and delete the redundent overload functions from 2011(using the function from super class). In the second one, we test the 2015 objective c counter and find some bugs. We read the source code and fixed the bugs(cyclomatic complexity counts different with 2014 baseline). | We make the objective c counter compatible with 2015 baseline. After read the source code, made the headers relationships in 2015 for future use.
7/14/16 - 7/20/16 | 8 | 1 | [5 empty] | 3 | [5 empty] | 4 | 4 |  | This week, we had 2 4-hour meetings. In the first one, we finished 10 test cases and test report from 2014 and found where the bug is which we found last week. In the second one, we finished other 10 test cases and finished the regression test for 2015 base line from 2011 test cases. | Although OBJC counter is inherent from C_CPP counter, there is several difference we need to concern and we will add OBJC keywords in it.
7/21/16 - 7/27/16 | 12 | 1 | [5 empty] | 2 | [5 empty] | 3 | 2 |  | This week, we have 1 4-hour meeting and 1 8-hour meeting. In the first one, we did the regression test from 2014 to 2015. In the second one, we add objective c together and write tests for them. Also, this week, we wrote the bug report for bugs we found in this semester. | Finished regression test and both 2014 and 2015 versions are compatible with objective c counter. Added objective c exclusive keywords in the counter.
7/28/16 - 8/3/16 | 8 | 2 | [5 empty] | 4 |  | 2 |  | 2 |  |  |  | 2 | This week, we have 2 4-hour meetings. In the first one, we finished our final report and the defeat log. In the second one, we fixed a bug we found these days for 2014 and found the same bug in 2015(cannot fix by now because it locates in common file) | Finished all tasks and documents required in the beginning of the semester. Logged all bugs and issues for future development.
3/23/16 - 3/29/16
3/30/16 - 4/5/16
4/6/16 - 4/12/16
4/13/16 - 4/19/16
4/20/16 - 4/26/16
Fill out your name and assigned project, and actual time spent in hours (or part of hour) for each activity for the weeks below. The time in this form IS NOT USED to determine your performance in the DR - as in, this will not determine the grade you receive for DR. Be honest in filling out the timesheet.