## Project Workplan
Objective C module Implementation and Test plan
| Date of Report | 2016-07-13
| Name | Project Plan (Object C UCC module )
| Description | The Cost Accounting project in support of the cost build-up requirement for the DoD IG proposal.
| Start Date | 2016-06-02 |  | End Date |  | 2016-08-03
Week | Task |  | Start Date | End Date | Target Completion date & Status | Comments
1. Compatible to 2014
1 | N/A
2 | Take familiar with framework and get clear about where to add funtionalities. Read the source code and documents of 2010 and 2011. |  | 2016-06-02 | 2016-06-08 | Yes | Have an overview of the project; Every one read the code of 2011 and documents;
3 | Read the code files of 2014 and add 2011 code files to 2014 |  | 2016-06-09 | 2016-06-15 | Yes | Merged 2011 OBJC source files to 2014; fixed some compile errors(48 errors); still working on fixing a linking errors; Drew a graph of header files to help understand the project framework; Make Trello for tracking tasks; (link is to the graph)
4 | Fix the linking error and make a test plan for 2014 version Objective C |  | 2016-06-16 | 2016-06-22 | Yes | We fixed the linking error and can successfully compile with 2014 baseline. We found that the 2011 Objective C functions were just copied the code from its superclass in baseline 2010. However there were many changes and improvements in the superclass from 2010 baseline to 2014 baseline. We think the counting functions in Objective C should be deprecated or updated using its superclass in 2014.
5 | Do regression test with 2014 baseline and make sure Objective C funtions work well. |  | 2016-06-23 | 2016-06-29 | Yes | 1. Fixed extfile problem of extensions sharing : need to specify extension files for OBJC, MATLAB and C_CPP languages(need to disccuss different approaches: ->h file for C_CPP and OBJC ; Drawback:count C_CPP need to specify all of extension files, C_CPP can't count .h by default, same with MATLAB; ->.h file is default for C_CPP and .m file is default for MATLAB; need to specify then for OBJC; Drawback: need C_CPP and MATLAB to ignore all of extension files for OBJC count ); 2. A problem: ->difftool: for all of the files with the exactly same code, not comapre all of them; 3.added Cyclomatic Complexity of OBJC in 2014 version; 4. finished some regression tests from 2011 (15/25);
6 | Do additional tests for 2014 Objective C functions |  | 2016-06-30 | 2016-07-06 | Yes | 1. Regression Test from Test 16 to Test 25 2. Write Cyclomatic Complexity Test Cases, do Cyclomatic Complexity Test from Test 1 to Test 8. 3. Change extfile specification file, user must specify all sharing language extension file names. 4. Problem: use extension file, user must flush all other share language extension file name first, then specify OBJC extension file name.
2. Compatible to 2015
7 | Make the code compatible to 2015 and fix bugs |  | 2016-07-07 | 2016-07-13 | Yes | 1. Make Objective C code compatible to 2015, delete the redundent functions from 2011 and add code to baseline 2015. 2. Test 4 basic regression cases in 2015, found some difference between 2014 and 2015 and fixed them. 2 bugs found in baseline 2015 1. C_CPP can only count "# define", "#define", but cannot count "# define" 2. int main(int a) and int main( int a) have different "int" count Problem: OBJC counter in 2011 just copied the code of C_CPP in 2011 and actually can only count SLOC, cyclomatic complexity and key words from c, cpp. It cannot count OBJC keywords(same in 2014).
8 | Do regression test with 2015 baseline and make sure Objective C funtions work well. |  | 2016-07-14 | 2016-07-20
9 | Do new feature tests from 2014 for 2015 baseline |  | 2016-07-21 | 2016-07-27
10 | Test code for 2015 |  | 2016-07-28 | 2016-08-03
| Baseline End Date | [5 empty] | 2016-08-03
Major Issues
Item No. | Description |  |  | Comments
1
2
3
4
Application Issues
| Description |  |  | Action Required By |  | Target Date
Process Issues
| Subject Area |  |  | Action Required By |  | Target Date
Resource Issues
| Subject Area |  |  | Action Required By |  | Target Date

## Performance Measure Template
All Measurements Used in the ESMS Database
| PM # | Performance Measure | BSC Framework | Strategic Goal or Objective per BSC or Strategic Plan | Army Performance Improvement Criteria (APIC) - 7 Major Categories Summarized Below | Major Organizational Unit | Function / Dept / Sub Group | Service or Product Line (if applicable) | METL Task | METL Sub-Task | Type of Measure | Measure Justification | Definition | Data Elements To Be Collected | Data Source | Data Collection Frequency D/W/M/Q/SA/A | PM Calculation Formula | Actual FY 03 | Actual FY 04 | Green Standard | Amber Standard | Red Standard | Primary Functional POC | Data Available? | Notes
Definition | What is the PM number for referencing. Could be LMR # or a unique number for local metrics? | What metric(s) should we use to measure whether we have met our requirements? | Is this measure a Customer, Process, Learn & Grow or Resources measure based on the BSC framework? | Insert major goals or objectives in this box as a reference in completing this template | 1) Formal Systems to Learn and Grow People 2) All Key processes are adding value 3) Strong focus on Customer Needs 4) Strategic Planning Process in Place 5) Leadership Effectiveness 6) Well Developed PMR is Followed 7) Key Performance Results in Place | Insert a list of the major organizational unit names in this box for reference in completing this template | Insert a Link here to reference back a list of Functions / Departments and other organizational units in completing this template | Insert the Operating Area such as Product or Service Line - To be used for Product Performance Analysis | What METL Task does the metric support? | What METL Sub-task does the metric support? | Is this measure a 1) Strategic 2) Operational 3) Tactical 4) Individual | Why are we using this metric? | How do we define this measure? | What are the data elements for caclulating the measure? | Where does the data reside? | How frequently should the data be collected? | What is the formula for calculating the measure? | What is the actual result of this measure for the Year 2003? | What is the actual result of this measure for the Year 2004? | What is the Green Threshold? | What is the Amber Threshold? | What is the Red Threshold? | Who is the primary owner for the measure and their email address? | Y/N | Are there any additional notes regarding the measure?
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
Note on N4: Measure Justification Criterial Meaningful: Measureable: Actionable: Input/Output/Outcome: Lead/Lag:

## Performance Measure Grading
Balanced Scorecard Project |  |  |  | Graded Attributes | Update Frequency / Repeatable | Degree of Reliability (Hard Data vs.Subjective) | Encourages the right behavior | Degree of Fit with Client's Culture | Degree of Support / Available Info |  |  | NonGraded Attributes | Leading or Lagging | Single or Index Metric
Quality Review of Metrics
Review and score all measurements used in your scorecard model | [9 empty] | Total Points | Overall Grade
Financial Objective (F1) | F1.1 | % Revenue Growth |  |  | 4 | 4 | 3 | 4 | 5 | 20 | 80% |  | Lagging | Single
| F1.2 | [8 empty] | 0 | 0%
| F1.3 | [8 empty] | 0 | 0%
| F1.4 | [8 empty] | 0 | 0%
Financial Objective (F2) | F2.1 | [8 empty] | 0 | 0%
| F2.2 | [8 empty] | 0 | 0%
| F2.3 | [8 empty] | 0 | 0%
| F2.4 | [8 empty] | 0 | 0%
Financial Objective (F3) | F3.1 | [8 empty] | 0 | 0%
| F3.2 | [8 empty] | 0 | 0%
| F3.3 | [8 empty] | 0 | 0%
| F3.4 | [8 empty] | 0 | 0%
Customer Objective (C1) | C1.1 | [8 empty] | 0 | 0%
| C1.2 | [8 empty] | 0 | 0%
| C1.3 | [8 empty] | 0 | 0%
| C1.4 | [8 empty] | 0 | 0%
Customer Objective (P2) | C2.1 | [8 empty] | 0 | 0%
| C2.2 | [8 empty] | 0 | 0%
| C2.3 | [8 empty] | 0 | 0%
| C2.4 | [8 empty] | 0 | 0%
Process Objective (P1) | P1.1 | [8 empty] | 0 | 0%
| P1.2 | [8 empty] | 0 | 0%
| P1.3 | [8 empty] | 0 | 0%
| P1.4 | [8 empty] | 0 | 0%
Process Objective (P2) | P2.1 | [8 empty] | 0 | 0%
| P2.2 | [8 empty] | 0 | 0%
| P2.3 | [8 empty] | 0 | 0%
| P2.4 | [8 empty] | 0 | 0%
Process Objective (P5) | P3.1 | [8 empty] | 0 | 0%
| P3.2 | [8 empty] | 0 | 0%
| P3.3 | [8 empty] | 0 | 0%
| P3.4 | [8 empty] | 0 | 0%
Process Objective (P4) | P4.1 | [8 empty] | 0 | 0%
| P4.2 | [8 empty] | 0 | 0%
| P4.3 | [8 empty] | 0 | 0%
| P4.4 | [8 empty] | 0 | 0%
L & G Objective (L1) | L1.1 | [8 empty] | 0 | 0%
| L1.2 | [8 empty] | 0 | 0%
| L1.3 | [8 empty] | 0 | 0%
| L1.4 | [8 empty] | 0 | 0%
L & G Objective (L2) | L2.1 | [8 empty] | 0 | 0%
| L2.2 | [8 empty] | 0 | 0%
| L2.3 | [8 empty] | 0 | 0%
| L2.4 | [8 empty] | 0 | 0%
L & G Objective (L3) | L3.1 | [8 empty] | 0 | 0%
| L3.2 | [8 empty] | 0 | 0%
| L3.3 | [8 empty] | 0 | 0%
| L3.4 | [8 empty] | 0 | 0%
Instructions:
Rate each Measurement for these attributes on a scale of 1 to 5:
1. Update Frequency: Measurement can get updated on a regular basis; M for Monthly, Q for Quarterly, A for Annual, etc.
2. Degree of Reliability: Can you easily measure the performance objective or is it too subjective when it comes to measurability.
3. Encourages the right behavior: Measurements should not confuse, distort, or create the wrong performance behavior within the Organization. Controllable?
4. Degree of Fit: Measurement fits with the culture and processes of Organization and flows well from Lower Level to Upper Level. (MACRO FIT - ORGANIZATIONAL)
5. Degree of Support: Client has existing procedures and processes that can support the measurement (such as available data is in place)
| Maximum Score |  | 25

## Powerpoint Slides
Alignment Matrix

## Team List
Project Roster
Name | Area | Location | Desk Phone | Cell Phone | Email
Project Intranet Web Site ► | www.intranets.com