## Project Workplan
Objective C module Implementation and Test plan
| Date of Report | 2016-06-06
| Name | Project Plan (Object C UCC module )
| Description | The Cost Accounting project in support of the cost build-up requirement for the DoD IG proposal.
| Start Date | 2016-06-02 |  | End Date |  | 2016-08-03
Week | Task |  | Start Date | End Date | Target Completion date & Status | Comments
1. Compatible to 2014
1 | N/A
2 | Take familiar with framework and get clear about where to add funtionalities. Read the source code and documents of 2010 and 2011. |  | 2016-06-02 | 2016-06-08
3 | Make code counter part for 2014 |  | 2016-06-09 | 2016-06-15
4 |  |  | 2016-06-16 | 2016-06-22
5 |  |  | 2016-06-23 | 2016-06-29
6 | Make diff tools for 2014 |  | 2016-06-30 | 2016-07-06
7 |  |  | 2016-07-07 | 2016-07-13
2. Compatible to 2015
8 | Make the code for 2015 and fix bugs |  | 2016-07-14 | 2016-07-20
9 |  |  | 2016-07-21 | 2016-07-27
10 | Final documents preparation |  | 2016-07-28 | 2016-08-03
| Baseline End Date | [5 empty] | 2016-08-03
Major Issues
Item No. | Description |  |  | Comments
1
2
3
4
Application Issues
| Description |  |  | Action Required By |  | Target Date
Process Issues
| Subject Area |  |  | Action Required By |  | Target Date
Resource Issues
| Subject Area |  |  | Action Required By |  | Target Date

## Performance Measure Template
All Measurements Used in the ESMS Database
| PM # | Performance Measure | BSC Framework | Strategic Goal or Objective per BSC or Strategic Plan | Army Performance Improvement Criteria (APIC) - 7 Major Categories Summarized Below | Major Organizational Unit | Function / Dept / Sub Group | Service or Product Line (if applicable) | METL Task | METL Sub-Task | Type of Measure | Measure Justification | Definition | Data Elements To Be Collected | Data Source | Data Collection Frequency D/W/M/Q/SA/A | PM Calculation Formula | Actual FY 03 | Actual FY 04 | Green Standard | Amber Standard | Red Standard | Primary Functional POC | Data Available? | Notes
Definition | What is the PM number for referencing. Could be LMR # or a unique number for local metrics? | What metric(s) should we use to measure whether we have met our requirements? | Is this measure a Customer, Process, Learn & Grow or Resources measure based on the BSC framework? | Insert major goals or objectives in this box as a reference in completing this template | 1) Formal Systems to Learn and Grow People 2) All Key processes are adding value 3) Strong focus on Customer Needs 4) Strategic Planning Process in Place 5) Leadership Effectiveness 6) Well Developed PMR is Followed 7) Key Performance Results in Place | Insert a list of the major organizational unit names in this box for reference in completing this template | Insert a Link here to reference back a list of Functions / Departments and other organizational units in completing this template | Insert the Operating Area such as Product or Service Line - To be used for Product Performance Analysis | What METL Task does the metric support? | What METL Sub-task does the metric support? | Is this measure a 1) Strategic 2) Operational 3) Tactical 4) Individual | Why are we using this metric? | How do we define this measure? | What are the data elements for caclulating the measure? | Where does the data reside? | How frequently should the data be collected? | What is the formula for calculating the measure? | What is the actual result of this measure for the Year 2003? | What is the actual result of this measure for the Year 2004? | What is the Green Threshold? | What is the Amber Threshold? | What is the Red Threshold? | Who is the primary owner for the measure and their email address? | Y/N | Are there any additional notes regarding the measure?
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
Note on N4: Measure Justification Criterial Meaningful: Measureable: Actionable: Input/Output/Outcome: Lead/Lag:

## Performance Measure Grading
Balanced Scorecard Project |  |  |  | Graded Attributes | Update Frequency / Repeatable | Degree of Reliability (Hard Data vs.Subjective) | Encourages the right behavior | Degree of Fit with Client's Culture | Degree of Support / Available Info |  |  | NonGraded Attributes | Leading or Lagging | Single or Index Metric
Quality Review of Metrics
Review and score all measurements used in your scorecard model | [9 empty] | Total Points | Overall Grade
Financial Objective (F1) | F1.1 | % Revenue Growth |  |  | 4 | 4 | 3 | 4 | 5 | 20 | 80% |  | Lagging | Single
| F1.2 | [8 empty] | 0 | 0%
| F1.3 | [8 empty] | 0 | 0%
| F1.4 | [8 empty] | 0 | 0%
Financial Objective (F2) | F2.1 | [8 empty] | 0 | 0%
| F2.2 | [8 empty] | 0 | 0%
| F2.3 | [8 empty] | 0 | 0%
| F2.4 | [8 empty] | 0 | 0%
Financial Objective (F3) | F3.1 | [8 empty] | 0 | 0%
| F3.2 | [8 empty] | 0 | 0%
| F3.3 | [8 empty] | 0 | 0%
| F3.4 | [8 empty] | 0 | 0%
Customer Objective (C1) | C1.1 | [8 empty] | 0 | 0%
| C1.2 | [8 empty] | 0 | 0%
| C1.3 | [8 empty] | 0 | 0%
| C1.4 | [8 empty] | 0 | 0%
Customer Objective (P2) | C2.1 | [8 empty] | 0 | 0%
| C2.2 | [8 empty] | 0 | 0%
| C2.3 | [8 empty] | 0 | 0%
| C2.4 | [8 empty] | 0 | 0%
Process Objective (P1) | P1.1 | [8 empty] | 0 | 0%
| P1.2 | [8 empty] | 0 | 0%
| P1.3 | [8 empty] | 0 | 0%
| P1.4 | [8 empty] | 0 | 0%
Process Objective (P2) | P2.1 | [8 empty] | 0 | 0%
| P2.2 | [8 empty] | 0 | 0%
| P2.3 | [8 empty] | 0 | 0%
| P2.4 | [8 empty] | 0 | 0%
Process Objective (P5) | P3.1 | [8 empty] | 0 | 0%
| P3.2 | [8 empty] | 0 | 0%
| P3.3 | [8 empty] | 0 | 0%
| P3.4 | [8 empty] | 0 | 0%
Process Objective (P4) | P4.1 | [8 empty] | 0 | 0%
| P4.2 | [8 empty] | 0 | 0%
| P4.3 | [8 empty] | 0 | 0%
| P4.4 | [8 empty] | 0 | 0%
L & G Objective (L1) | L1.1 | [8 empty] | 0 | 0%
| L1.2 | [8 empty] | 0 | 0%
| L1.3 | [8 empty] | 0 | 0%
| L1.4 | [8 empty] | 0 | 0%
L & G Objective (L2) | L2.1 | [8 empty] | 0 | 0%
| L2.2 | [8 empty] | 0 | 0%
| L2.3 | [8 empty] | 0 | 0%
| L2.4 | [8 empty] | 0 | 0%
L & G Objective (L3) | L3.1 | [8 empty] | 0 | 0%
| L3.2 | [8 empty] | 0 | 0%
| L3.3 | [8 empty] | 0 | 0%
| L3.4 | [8 empty] | 0 | 0%
Instructions:
Rate each Measurement for these attributes on a scale of 1 to 5:
1. Update Frequency: Measurement can get updated on a regular basis; M for Monthly, Q for Quarterly, A for Annual, etc.
2. Degree of Reliability: Can you easily measure the performance objective or is it too subjective when it comes to measurability.
3. Encourages the right behavior: Measurements should not confuse, distort, or create the wrong performance behavior within the Organization. Controllable?
4. Degree of Fit: Measurement fits with the culture and processes of Organization and flows well from Lower Level to Upper Level. (MACRO FIT - ORGANIZATIONAL)
5. Degree of Support: Client has existing procedures and processes that can support the measurement (such as available data is in place)
| Maximum Score |  | 25

## Powerpoint Slides
Alignment Matrix

## Team List
Project Roster
Name | Area | Location | Desk Phone | Cell Phone | Email
Project Intranet Web Site ► | www.intranets.com